## Sheet1
[6 empty] | 1 qtr 2019 |  |  | 2 qtr 2019 |  |  | 3 qtr 2019 |  |  | 4 qtr 2019 |  |  | 1 qtr 2020 |  |  | 2 qtr 2020 |  |  | 3 qtr 2020 |  |  | 4 qtr 2020
Goal | Strategy |  | Responsible | Time Frame | Project Scope | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
1. Be the influential voice for home care
Be the influential voice for home care | Increase advocacy | 1. Increase advocacy
Be the influential voice for home care | Increase advocacy | a. Grow awareness of advocacy importance by developing and implementing a grassroots campaign to increase advocacy center actions, attendance at MHCA Day at the Capitol and legislative visits with clients. | M.R./K.M. | 4Q20 | LG - XLG
▪ Work with Legislative Committee to develop a grassroots plan that includes short-term measurable goals | bar: 1 qtr 2019 M to 2 qtr 2019 M
▪ Assign responsibilities and begin implementation of the grassroots plan | bar: 3 qtr 2019 J to 2 qtr 2020 M
▪ Develop & implement an enhanced promo/recruitment plan to increase attendance at 2020 Day at the Capitol | bar: 4 qtr 2019 O to 1 qtr 2020 F; 4 qtr 2020 O to 4 qtr 2020 D
|  | ▪ Monitor Develop tracking mechanism for Legislator/Member visits utilizing tracking mechanism | M.R. | bar: 2 qtr 2019 J; 1 qtr 2020 F; 2 qtr 2020 A; 4 qtr 2020 N to 4 qtr 2020 D
Be the influential voice for home care | Increase advocacy | b. Increase member communications around legislative and regulatory issues that are timely and include key points. | M.R. | 2Q19 | SM
|  | ▪ Develop an Action Alert email template. |  | 1Q19 | bar: 1 qtr 2019 M
▪ Create protocol regarding when state and federal policy alerts should be sent. | bar: 1 qtr 2019 M to 2 qtr 2019 M
Be the influential voice for home care | Increase advocacy | c. Increase transparency of MHCA agenda and activities to committee members | K.M. | 3Q19 | SM
|  | ▪ Orient Committee Chairs |  | 3Q19 | bar: 3 qtr 2019 J to 3 qtr 2019 S
|  | ▪ Include advocacy update on committee agendas | KM, MR, MS, KP | 3Q19 | bar: 3 qtr 2019 J to 3 qtr 2019 S; 1 qtr 2020 J to 4 qtr 2020 D
▪Determine plan for what is covered in updates | bar: 3 qtr 2019 J to 3 qtr 2019 S
Be the influential voice for home care | Increase advocacy | d. Develop workplan for workforce advocacy | K.M. | 4Q20 | LG
▪ Draft a plan that includes working with academic programs & legislators | bar: 3 qtr 2019 A to 3 qtr 2019 S
▪ Review plan with Workforce Workgroup | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪ Begin Implementation of the plan | bar: 4 qtr 2019 N to 2 qtr 2020 M
Be the influential voice for home care | Increase advocacy | e. Develop a plan and advocate for home care payment reform that creates a sustainable reimbursement framework, including alignment with minimum wages. | K.M. | 3Q19 | XLG
▪ Determine model for visit rates (using a percentage of LUPA rates) | bar: 1 qtr 2019 J to 1 qtr 2019 F
▪ Identify a reimbursement model for HCN hourly rates | bar: 2 qtr 2019 M to 3 qtr 2019 J
▪ Seek DHS' technical assistance | bar: 3 qtr 2019 J to 3 qtr 2019 S
▪ Draft a bill using a percentage of LUPA rates for visits. | bar: 3 qtr 2019 J to 3 qtr 2019 S
▪ Identify & implement plan for seeking support from legislators | bar: 4 qtr 2019 O to 2 qtr 2020 M
Be the influential voice for home care | Be a creditable voice | 2. Be a credible voice
Be the influential voice for home care | Be a creditable voice | a. MHCA continues to be viewed as expert advisor for MDH & DHS | K.M. | ON-GOING | XLG
▪ Executive Director further develop relationships with agency leaders, with emphasis on new Commissioners and directors
▪ Continue to participate in the quarterly stakeholder meetings with MDH | bar: 1 qtr 2019 J; 2 qtr 2019 A; 3 qtr 2019 J; 4 qtr 2019 O; 1 qtr 2020 J; 2 qtr 2020 A; 3 qtr 2020 J; 4 qtr 2020 O
▪ Board members seek out agency staff at MHCA conferences | bar: 2 qtr 2019 M; 4 qtr 2019 O; 2 qtr 2020 M; 4 qtr 2020 O
Be the influential voice for home care | Be a creditable voice | b. Form alliances to strengthen voice for all of home care | K.M. | ON-GOING | XLG
|  | ▪ Dialogue with MNHPC about collaboration or affiliation |  |  |  | 3 qtr 2019 A: N/A; 4 qtr 2019 N: N/A
|  | ▪ Discuss closer collaboration with MN First Provider Alliance |  |  |  | 4 qtr 2019 D: On Hold
Enhance member value |  | 2. Enhance member value |  | Time Frame
Enhance member value | Increase member resources | 1. Increase member resources
Enhance member value | Increase member resources | a. Increase expert assistance through in-house staff. | K.M. | 3Q19 | LG
▪ Finalize job description for new position | bar: 1 qtr 2019 J to 1 qtr 2019 M
▪ Seek and hire candidate | bar: 2 qtr 2019 A to 3 qtr 2019 J
Enhance member value | Increase member resources | b. Explore expansion of nurse consultants’ program to include on-site services. | K.P. | 3Q20 | LG
▪ Query members to identify additional consultant needs | bar: 3 qtr 2020 J to 3 qtr 2020 A
▪ Develop ideas for consideration that reflect members' needs | bar: 3 qtr 2020 S to 4 qtr 2020 O
Enhance member value | Increase member resources | c. Identify needs & work toward development of additional resources that are on-demand and delivered in timely manner. | K.P. | 2Q20 | XLG
▪ Survey members | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪ Work with appropriate committees to create a plan, with priority levels | bar: 4 qtr 2019 N to 1 qtr 2020 M
▪ Create plan for and develop Palliative Care resource | bar: 2 qtr 2020 J; 3 qtr 2020 A to 4 qtr 2020 O
▪ Begin resource development, within budgeted means | bar: 1 qtr 2020 F to 2 qtr 2020 M
▪ Budget for additional resources | bar: 3 qtr 2020 S to 4 qtr 2020 O
Enhance member value | Increase member resources | d. Explore member group discount program. | M.R. | 2Q20 | LG/XLG
▪ Determine interest in discount programs via Membership Survey | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪ Compile inventory of potential discount programs via state association survey | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪Member Relations & Education Committee evaluate programs to determine which may be of interest to members | bar: 4 qtr 2019 N; 2 qtr 2020 A to 2 qtr 2020 M
▪Seek input from Board of Directors | bar: 3 qtr 2020 J
▪Obtain Board of Directors approval for selected programs
▪Develop launch plan for new programs | bar: 3 qtr 2020 S to 4 qtr 2020 O
Enhance member value | Enhance region meetings | 2. Enhance region meeting
Enhance member value | Enhance region meetings | a. Continue new format | DONE | DONE | SM
Enhance member value | Enhance region meetings | b. Seek member input | M.R. | 2Q19 | MED
▪ Board Members attend Region Meetings in May to have dialogue & collect data on value of meetings. | bar: 2 qtr 2019 M
▪ Collect and compile data received from Board of Directors/Region Leaders | bar: 2 qtr 2019 M to 2 qtr 2019 J
▪ Develop implementation plan | bar: 3 qtr 2019 J to 3 qtr 2019 A
Enhance member value | Enhance region meetings | c. Provide increased admin support | M.R. | 1Q19 | SM
▪ Compile and distribute meeting agendas | bar: 1 qtr 2019 J to 1 qtr 2019 F
Enhance member value | Enhance region meetings | d. Develop a plan that includes MHCA volunteer leadership attending mtgs | M.R. | 2Q19 | LG
▪ Reinforce expectation that committee members attend Region Meetings | bar: 3 qtr 2019 J
▪ Determine schedule for committee visits - aim to have applicable committees assigned to each meeting | bar: 3 qtr 2019 A to 3 qtr 2019 S
▪ Work with Committee Liaison and Chair to develop talking points | bar: 3 qtr 2019 S; 4 qtr 2019 D
Enhance member value | Increase accessible education | 3. Increase accessible education
Enhance member value | Increase accessible education | a. Align educational options with member needs, developing more accessible or virtual meetings. | M.S. | 3Q19 | XLG
▪ Gather member feedback regarding educational needs for 2020 from Education Survey | bar: 2 qtr 2019 J
▪ Gather member feedback regarding educational needs for 2020 from committee | bar: 3 qtr 2019 A
▪ Offer hospice education through conference sessions that cross over with home care and state share webinars, as available | bar: 1 qtr 2020 J to 1 qtr 2020 F; 4 qtr 2020 N to 4 qtr 2020 D
▪ Develop an education calendar for 2020 that utilizes more webinars than workshops | bar: 3 qtr 2019 S
Enhance member value | Increase accessible education | b. Evaluate RCTC and identify ways to improve program or seek other options. | M.S. | 4Q20 | XLG
▪ Identify education needed by members | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪ Identify possible partnerships | bar: 4 qtr 2019 O to 4 qtr 2019 D
▪ Research options | bar: 1 qtr 2020 J to 1 qtr 2020 M
▪ Contact and negotiate a new partnership agreement | bar: 3 qtr 2020 J to 3 qtr 2020 S
Enhance member value | Increase accessible education | c. Create multiple lower cost education offerings | M.S. | 3Q19 | MED
▪ Complete a cost comparison with other Associations and align budget with industry standard | bar: 3 qtr 2019 S
Strengthen org health & sustainability |  | 3. Strengthen organizational agility, health & sustainability |  | Time Frame
Strengthen org health & sustainability | Increase dues revenue | 1. Increase dues revenue
Strengthen org health & sustainability | Increase dues revenue | a. Identifying data to prove provider and business partner member value and integrate into recruitment plan and materials | M.R. | 1Q20 | XLG
|  | ▪ Conduct 12-month study on MDH surveys to determine deficiency/citation rate of members vs. non-members | K.P. | bar: 1 qtr 2020 F to 2 qtr 2020 A
▪ Identify which member benefits are of highest value to current members via membership survey | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪ Convene focus group of Provider members to determine value | bar: 2 qtr 2020 M to 3 qtr 2020 J
▪ Convene focus group of Business Partner members to determine value | bar: 2 qtr 2020 M to 2 qtr 2020 J
▪ Compile above findings into a member recruitment/retention plan and a member value document | bar: 3 qtr 2020 J to 3 qtr 2020 A
Strengthen org health & sustainability | Increase dues revenue | b. Informing MDH surveyors of MHCA benefits to increase referrals | K.M. | 1Q20 | MED
▪ Share a member value document with MDH surveyors and ask them to continue encouraging providers to join MHCA | bar: 3 qtr 2020 S to 4 qtr 2020 O
Strengthen org health & sustainability | Increase dues revenue | c. Implement updated recruitment and retention plans | M.R. | 2Q20 | LG | bar: 3 qtr 2020 S to 4 qtr 2020 O
Strengthen org health & sustainability | Increase dues revenue | d. Study industry trends and identify member categories and a dues structure that are in alignment | M.R. | 4Q20 | XLG
▪ Compile inventory of state home care association dues structures | bar: 4 qtr 2020 N to 4 qtr 2020 D
▪ Compile inventory of MN comparable trade association dues structures | bar: 4 qtr 2020 N to 4 qtr 2020 D
▪ Determine whether dues structure changes are warranted and, if so, develop a plan for 2022 | bar: 4 qtr 2020 N to 4 qtr 2020 D
Strengthen org health & sustainability | Increase non-dues revenue | 2. Increase non-dues revenue
Strengthen org health & sustainability | Increase non-dues revenue | a. Increase educational partnerships | M.S. | ON-GOING | MED
▪ Identify MHCA hosted webinars that could be marketed to other state home care associations | bar: 3 qtr 2019 A; 3 qtr 2020 A
▪ Send out marketing materials for MHCA webinar revenue shares between states | bar: 4 qtr 2019 O to 4 qtr 2019 D; 4 qtr 2020 O to 4 qtr 2020 D
▪ Continue to identify and participate in revenue shares offered by other state home care associations that our members would benefit from
▪ Offer MHCA education to ND and WI providers, as agreed upon by those states | bar: 3 qtr 2020 J to 3 qtr 2020 A
Strengthen org health & sustainability | Increase non-dues revenue | b. Seek affinity programs | M.R. | 4Q20 | LG
▪ Compile inventory of potential affinity programs via state association survey | bar: 3 qtr 2019 S to 4 qtr 2019 O
▪ Determine member interest in potential affinity programs via Membership Survey | bar: 3 qtr 2020 S to 4 qtr 2020 O
▪ Membership Committee evaluate programs to determine which are best suited to association | bar: 4 qtr 2020 N to 4 qtr 2020 D
Strengthen org health & sustainability | develop agile organizational culture | 3. Develop agile, healthy and sustainable organizational culture
Strengthen org health & sustainability | develop agile organizational culture | a. Be approachable, forward-thinking and an advocate | ALL STAFF | ON-GOING | SM | bar: 1 qtr 2019 J; 2 qtr 2019 A; 3 qtr 2019 J; 4 qtr 2019 O; 1 qtr 2020 J; 2 qtr 2020 A; 3 qtr 2020 J; 4 qtr 2020 O
Strengthen org health & sustainability | develop agile organizational culture | b. Restructure teams to align with MHCA’s evolution | K.M. | 2Q19 | LG
▪ Present proposal to board | bar: 1 qtr 2019 M
▪ Finalize and implement new structure | bar: 2 qtr 2019 A to 2 qtr 2019 M
Strengthen org health & sustainability | develop agile organizational culture | c. Develop opportunities to engage new leaders | M.R. | 2Q20 | LG
▪ Identify a Vice Chair for each committee, aiming to tap a new leader | bar: 2 qtr 2019 M
▪ Develop plan to identify up-and-coming leaders within member agencies | bar: 2 qtr 2020 A
▪ Work with Region Leaders to develop leadership recruitment plan | bar: 2 qtr 2020 M