## Sheet1
|  |  | 1st quarter 2022 |  |  | 2nd quarter 2022 |  |  | 3rd quarter 2022 |  |  | 4th quarter 2022
| Responsible | Project Scope | J | F | M | A | M | J | J | A | S | O | N | D
1. Be the influential voice for home care
a. Medicaid Reform – Advocate for funding to stabilize the Home Care Access Infrastructure | K.M. | XLG | bar: 1st quarter 2022 J to 2nd quarter 2022 M
b. Strengthen relationships with lawmakers through grassroots champions; Identify at least one MHCA member as a primary constituent/contact for each state Health and Human Services committee member. | M.R./K.M. | MED | bar: 1st quarter 2022 J to 1st quarter 2022 F; 4th quarter 2022 O
c. Support federal payment reform initiatives and increase grassroots support of the legislation (measured by 10% increase from 2021 member usage of the Advocacy Center) | B.L./M.R. | LG | bar: 1st quarter 2022 J; 2nd quarter 2022 A; 3rd quarter 2022 J; 4th quarter 2022 O
d. Work collaboratively to educate and provide information on value-based reimbursement models to providers, lawmakers and DHS. | B.L./K.M. | XLG | bar: 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Create an overview document for external audience | B.L./K.M. | MED | bar: 2nd quarter 2022 J to 3rd quarter 2022 S
▪ Provide tools for providers (video, quarterly updates) | B.L.K.M. | LG | bar: 1st quarter 2022 M to 3rd quarter 2022 A; 4th quarter 2022 O
e. Develop relationships with Medicare Advantage plans, with intent to explore partnerships. (UHC, HealthPartners) | K.M./B.L. | XLG | bar: 3rd quarter 2022 J to 3rd quarter 2022 S
f. Increase awareness of home care career opportunities to current and prospective nurses | K.M. | XLG
▪ Develop opportunities to network with students through HOSA and guest speaking in nursing classes. | K.M. | LG | bar: 1st quarter 2022 F; 2nd quarter 2022 A to 2nd quarter 2022 M; 3rd quarter 2022 S to 4th quarter 2022 O
▪ Expand the provider toolkit/guide and promote nursing clinical experience opportunities. | B.L./K.M. | XLG | bar: 1st quarter 2022 M to 3rd quarter 2022 J
▪ Maintain and share a current list of agencies & schools interested in clinical experiences | M.S./A.F. | MED | bar: 1st quarter 2022 F; 3rd quarter 2022 S
▪ Explore ideas for expanding Workforce Workgroup membership, to include more partners | K.M. | MED | bar: 3rd quarter 2022 J
g. Develop general orientation materials to support member agencies | B.L. | LG | bar: 1st quarter 2022 M to 3rd quarter 2022 S
h. Secure funding and consultant; develop and implement PR campaign to promote broad scope of home care careers | M.R./K.M. | XLG | bar: 1st quarter 2022 F to 2nd quarter 2022 J
i. Maintain/build relationships with MACN and AD/PN Association (annual mtgs) | K.M. | XLG | bar: 2nd quarter 2022 M; 3rd quarter 2022 S
|  |  | 1st quarter 2022 |  |  | 2nd quarter 2022 |  |  | 3rd quarter 2022 |  |  | 4th quarter 2022
| Responsible | Project Scope | J | F | M | A | M | J | J | A | S | O | N | D
2. Enhance Member Resources
a. Develop member resources and programs that increase the value of membership | M.R. | LG | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Identify and roll-out education and training opportunities to assist providers in catching up when waivers are expiring (e.g. CPR) | B.L./M.S. | LG | bar: 1st quarter 2022 F
▪ Provide Value Based Purchasing education for providers | M.S. | MED | bar: 2nd quarter 2022 M; 4th quarter 2022 O
▪ Develop telehealth toolkit, with roadmap, costs, payment & reimbursement information | B.L. | LG | bar: 2nd quarter 2022 M to 2nd quarter 2022 J
b. Enhance educational opportunities that increase the value of membership. | M.S. | LG | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Study member needs for home care aide or CNA Training | M.S. | LG | bar: 2nd quarter 2022 A
▪ Host Telehealth Summit | M.S. | MED | bar: 2nd quarter 2022 A
|  |  | 1st quarter 2022 |  |  | 2nd quarter 2022 |  |  | 3rd quarter 2022 |  |  | 4th quarter 2022
| Responsible | Project Scope | J | F | M | A | M | J | J | A | S | O | N | D
3. Develop an Equity Journey Roadmap for MHCA
a. Integrate equity journey into all education. | M.S. | MED | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Consider equity as speakers are selected for MHCA events | M.S. | SM | bar: 2nd quarter 2022 J; 4th quarter 2022 O
▪ Create leadership development opportunities | M.S. | MED | bar: 2nd quarter 2022 J; 4th quarter 2022 O
b. Offer DEI education including implicit bias. | M.S. | SM | bar: 2nd quarter 2022 J; 4th quarter 2022 O
c. Consider offering education & resources in multiple languages | M.S. | LG | bar: 4th quarter 2022 O
▪ Survey members to ascertain needs | M.S. | SM | bar: 3rd quarter 2022 S
▪ Research options to meet needs | M.S. | LG | bar: 4th quarter 2022 D
|  |  | 1st quarter 2022 |  |  | 2nd quarter 2022 |  |  | 3rd quarter 2022 |  |  | 4th quarter 2022
| Responsible | Project Scope | J | F | M | A | M | J | J | A | S | O | N | D
4. Strengthen organizational agility, health and sustainability
a. Maintain and grow an agile, healthy and sustainable organizational culture | K.M. | LG
▪ Ensure equity journey value is considered when developing member resources | ALL | MED | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Implement plan to identify up-and-coming volunteer leaders | M.R. | MED | bar: 1st quarter 2022 M to 2nd quarter 2022 M
b. Increase dues revenue | M.R. | LG
▪ Create & implement targeted recruitment plan, including former member agencies and Medicare certified agencies | M.R. | MED | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Monitor state lists to recruit new agencies | M.R. | SM | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
▪ Continual review of member value enhancements | M.R. | SM | bar: 1st quarter 2022 M; 2nd quarter 2022 J; 3rd quarter 2022 S; 4th quarter 2022 D
c. Monitor and increase non-dues revenue through program promotion and expansion | M.R. | LG | bar: 1st quarter 2022 F; 2nd quarter 2022 A; 3rd quarter 2022 J; 4th quarter 2022 O
LEGEND
Small
§ 1 staff; 1-2 weeks
Medium
§ 1 staff; 1 month OR
§ 2 staff; 2 weeks
Large
§ 1-2 staff + member involvement
X-Large
§ Involves external stakeholders, Board and/or Executive Director