## Sheet1
MHCA Strategic Plan 2024 |  | 1st quarter 2024 |  |  | 2nd quarter 2024 |  |  | 3rd quarter 2024 |  |  | 4th quarter 2024
| Responsible | J | F | M | A | M | J | J | A | S | O | N | D
1. Be the influential voice for home care
a. Strengthen state advocacy efforts | KM
▪ Identify MHCA priority legislative issues | KM | bar: 3rd quarter 2024 A to 3rd quarter 2024 S
▪ Work with Lobbyist to advocate for MHCA bills to be heard and passed in committee hearings. | KM | bar: 1st quarter 2024 J to 1st quarter 2024 M
▪ Increase communications with all legislators at the beginning of the 2024 session by 15% (81 emails) | BL | bar: 1st quarter 2024 J
▪ Assign at least one MHCA member to each Health and Human Services Committee member, as a Grassroots Champion. | BL | bar: 1st quarter 2024 J
▪ Increase messages sent through our advocacy center by 15% by the end of the 2023 legislative session (317 messages) and maintain 1,000+ for the 2024 session | BL | bar: 2nd quarter 2024 M
▪ Increase participation in 2023 Day at the Capitol by 20% and by 10% for the 2024 DAC | BL | bar: 1st quarter 2024 M
▪ Advocate with legislative leaders for inclusion in the Omnibus bill, as applicable | KM/BL | bar: 1st quarter 2024 M to 2nd quarter 2024 M
b. Meet with all MN Congressional offices annually | KM | bar: 1st quarter 2024 M; 4th quarter 2024 O to 4th quarter 2024 D
c. Payer Liaision Workgroup meet with two additional payers | BL
▪ Share insights with MHCA members through Informer and listservs | BL | bar: 1st quarter 2024 M; 2nd quarter 2024 J; 3rd quarter 2024 S; 4th quarter 2024 D
▪ Meet with Medica (if not done in 2023) | BL
▪ Meet with Blue Cross Blue Shield or another payer | BL | bar: 2nd quarter 2024 M
d. Build awareness of home care careers through presentations to high schoolers | KM
▪ Promote home care presentations to HOSA chapters | KM | bar: 2nd quarter 2024 A; 3rd quarter 2024 S
▪ Present to at least 2 HOSA Chapters | KM | bar: 2nd quarter 2024 M; 4th quarter 2024 D
▪ Participate in at least 3 Scrubs camps | bar: 2nd quarter 2024 M to 3rd quarter 2024 J
e. Develop relationships with nursing programs to build awareness of home care careers | LW
▪ Encourage schools to host MHCA in a nursing class or a student nursing organization | LW | bar: 1st quarter 2024 J to 1st quarter 2024 F; 3rd quarter 2024 A to 3rd quarter 2024 S
▪ Present to 2+ nursing programs (new from 2022): St. Benedict's/St. John's | bar: 1st quarter 2024 J to 1st quarter 2024 F; 3rd quarter 2024 S to 4th quarter 2024 D
▪Expand the number of home care clinical sites by encouraging members to participate and sharing the clinical site list with schools at least annually | LW | bar: 1st quarter 2024 J to 1st quarter 2024 M; 3rd quarter 2024 J to 3rd quarter 2024 S
2.Maximize Member Engagement
a. New members will access and value at least 4 resources | DA
▪ Hold orientation for each new member, offering deeper walkthrough of resources and education from BL and/or MS | DA | bar: 1st quarter 2024 F; 2nd quarter 2024 M; 3rd quarter 2024 A; 4th quarter 2024 N
▪ Survey new members to discover which resources they accessed and the perceived value | DA | bar: 4th quarter 2024 D
b. Increase participation in member meet up groups by 10% | BL | bar: 4th quarter 2024 D
c. Offer 43+ educational sessions | MS
▪ Work with MRE Committee to schedule webinars, workshops, and conference sessions | MS | bar: 3rd quarter 2024 A to 4th quarter 2024 O
d. Implement Net Promoter Score | DA/KM
▪ Determine what the net promoter score will measure this year | DA/KM | bar: 3rd quarter 2024 J to 3rd quarter 2024 S
▪ Survey members with net promoter score question | DA/KM | bar: 4th quarter 2024 O
e. Plan Region/Member Meetings TBD, based on survey results | DA/MS
▪ Determine 2024 Member Meeting format & schedule meetings | DA/MS | bar: 1st quarter 2024 J
▪ Work with MRE Committee to schedule breakout session topics that will be beneficial to all member types | DA/MS | bar: 1st quarter 2024 M; 2nd quarter 2024 J; 4th quarter 2024 O; 4th quarter 2024 D
f. Increase member listserv usage by 10% | DA/BL | bar: 4th quarter 2024 D
▪ Promote listservs in member communications twice per quarter | DA/BL | bar: 1st quarter 2024 M; 2nd quarter 2024 M; 3rd quarter 2024 J; 3rd quarter 2024 S; 4th quarter 2024 D
g. Plan and implement regional social hour at Annual Meeting TBD, based on evals | DA/MS | bar: 3rd quarter 2024 S to 4th quarter 2024 O
h. Identify gaps in member resources and update current resources. | BL
▪ Create 5 new member resources each year. | BL | bar: 1st quarter 2024 M; 2nd quarter 2024 J; 3rd quarter 2024 S; 4th quarter 2024 D
i. Work with the "DEI" committee to develop 2-4 initiatives that will focus on increasing MHCA leaders that are more fully representative of the industry. | DA/KM | bar: 4th quarter 2024 O
3. Foster meaningful connections & elevate opportunities
a. MHCA offer at least 3 volunteers for 2023 HOSA competition and 5 volunteers for 2024 | KM
▪ Promote opportunities with volunteers and staff | KM | bar: 1st quarter 2024 F; 4th quarter 2024 O
▪ Volunteers for Spring HOSA Judging | KM | bar: 1st quarter 2024 M
▪ Participation in Fall HOSA Convention | KM | bar: 4th quarter 2024 N
b. Offer at least 6 revenue shares with other home care associations | MS
▪ Work with MRE Committee to schedule virtual education that can be shared with our state partners | MS | bar: 2nd quarter 2024 A to 2nd quarter 2024 J
c. Meet with MNHPC two times in 2024 to share priority issues and discuss potential collaboration | KM | bar: 2nd quarter 2024 M; 4th quarter 2024 N
d. Continued outreach effort to WI Home Care Association to discuss possible education sharing | KM | bar: 1st quarter 2024 F
e. Explore scope and intersection of community paramedicine and home care, along with potential collaboration opportunities. | KM | bar: 1st quarter 2024 J
f. Collaborate with MN POLST to expand usage and visable posting of POLST forms in homes. | bar: 1st quarter 2024 F
4. Strengthen organizational agility, health and sustainability
a. Increase dues revenue | DA
▪ Recruit 15 new members | DA | bar: 1st quarter 2024 F; 2nd quarter 2024 M; 3rd quarter 2024 A; 4th quarter 2024 D
▪ Utilize 5 touch recruitment plan | DA | bar: 1st quarter 2024 F; 2nd quarter 2024 M; 3rd quarter 2024 A; 4th quarter 2024 D
▪ Identify and connect with members who have not participated in education or a meetup, and are not serving on a committee. | DA | bar: 2nd quarter 2024 J; 4th quarter 2024 N
b. Increase non-dues revenue by adding at least one new revenue source | DA/BL
▪ Identify the new source | DA/BL | bar: 2nd quarter 2024 J
▪ Implement / roll out the new program/resource | DA/BL | bar: 3rd quarter 2024 A
c. Study sponsorship program structure and implement proposed changes | DA | bar: 4th quarter 2024 O
▪ Increase program revenue by 10% | bar: 4th quarter 2024 O
d. Study membership structure | DA
▪ Work with MRE to review current membership structure and study additional categories | DA | bar: 2nd quarter 2024 M; 4th quarter 2024 D
e. Manage MHCA website content | LW
▪ Review & update website pages every quarter | LW | bar: 1st quarter 2024 M; 2nd quarter 2024 J; 3rd quarter 2024 S; 4th quarter 2024 D
f. Enhance board development | KM
▪ Discuss & implement board self - evaluation with the board | KM | bar: 4th quarter 2024 N
▪ Consider other board development enhancements | KM | bar: 1st quarter 2024 F
g. Review Policies annually and make appropriate updates (move to winter) | KM | bar: 1st quarter 2024 J